## Start Here
Project Schedule | Tasks, timelines and ARCI to meet the project goals and deliverables to be completed at the outset of the project. Depending on the nature of the project, past project plans may be useful in populating the Schedule incorporating tasks as well as Action Items identified throughout the course of the project
Project Goals | Goals for the project and tracking of progress towards them; established and approved during the project proposal
Action Items | Tracks action items that aren't built into the Project Schedule as tasks. Helps to manage items that emerge and document for future project plan integration
Decisions Made | Source of truth for decisions made relating to the project at the outset and throughout the course of the project
RAID - Risks, Assumptions, Issues & Dependencies | Documents risks, assumptions, issues and dependencies relating to the project to review regularly and mitigate
Roles | Aligns on team members' role in the project and their participation as either Core or Extended Team
Meeting Minutes | Template for meeting minutes of regular Project Plan meetings. Usually captured in separate Google Document linked here
Status Update | Template for regular Slack updates on the project to the Core and Extended team. Usually used as a Slack Workflow.
Inputs | Variables used throughout the project plan. You will need to update team member names as the project team is established
ADDITIONAL INFORMATION & RESOURCES
Project Brief | Template proposal which should become the source of truth for key project details
Project Charter | Document that formally recognizes the existence of a project and provides a summary of a project's objective and management
Kick-Off Deck | Template Kick-Off Deck for use at the beginning of each project
Project Folder | Link to the Google Drive project folder intended to house all project related documents
Video Testimonials | Folder full of video testimonials from our learners
Best Annual Reports & Best practices | Article with some examples of great annual reports
Giving Levels _ Fundraising | Information on what is promised to certain funders. Relevance: 10K+ donors need to be called out in annual report
Jamboard | From the Blue Sky kick off meeting
CLC Sponsors Page | Will need to be updated as Annual Report goes live

## Project Schedule
.
[9 empty] | Project Start Date: |  | 2022-04-26
[9 empty] | Display Week: |  | 1 |  | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13 | [6 empty] | 2022-06-20 | [6 empty] | 2022-06-27 | [6 empty] | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22 | [6 empty] | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26
 | time axis 2022-04-25 to 2022-10-02
# | TASKS | RELATED DOCS | ACCOUNTABLE | RESPONSIBLE | CONSULTED | INFORMED | PROGRESS | % | START | DAYS | END | time axis 2022-04-25 to 2022-10-02
1 | PROJECT INITIATION | [5 empty] | 90% |  | 2022-04-26 |  | 2022-05-20
1.1 | Project team assembled |  |  | Fanny | Erin |  | 100% |  | 2022-04-26 | 1 | 2022-04-27
1.2 | Project channel created |  | Nancy | Erin |  |  | 100% |  | 2022-04-27 | 0 | 2022-04-27
1.3 | Brief created |  | Nancy | Erin |  |  | 100% |  | 2022-04-27 | 0 | 2022-04-27
1.4 | Brief reviewed by team |  | Fanny | Project Team |  |  | 100% |  | 2022-04-27 | 21 | 2022-05-18
1.5 | Brief edits made |  | Nancy | Fanny | Layah |  | 100% |  | 2022-05-18 | 1 | 2022-05-19
1.6 | Blue sky kick-off meeting |  | Nancy | Fanny |  | Project Team | 100% |  | 2022-05-17 | 0 | 2022-05-17
1.7 | Brief Finalized by Marketing Mgr |  | Erin | Layah |  |  | 100% |  | 2022-05-30 | 0 | 2022-05-30
1.8 | Brief approved |  | Fanny | Nancy |  |  | 100% |  | 2022-05-19 | 0 | 2022-05-19
1.9 | Project Schedule complete |  | Fanny | Erin |  |  | 90% |  | 2022-04-27 | 23 | 2022-05-20
1.10 | Project Success Criteria Determined | Slack | Nancy | Fanny | Erin | Project Team | 100% |  | 2022-05-12 | 7 | 2022-05-19
1.11 | Sign off on Stage Completed | [5 empty] | 0% |  |  | 0
2 | PROJECT PLANNING | [5 empty] | 22.22% |  |  | 0
2.1 | Risk Management Plan Created |  | Fanny | Erin | Project Team |  | 0% |  | 2022-05-19 | 5 | 2022-05-24
2.2 | Project Communications Management plan created |  | Fanny | Erin |  | Project Team | 0% |  | 2022-05-19 | 5 | 2022-05-24
2.3 | Stakeholder Management plan created |  | Fanny | Erin | Cait B |  | 0% |  | 2022-05-19 | 5 | 2022-05-24
2.4 | Creative development plan created |  | Nancy | Layah |  |  | 0% |  | 2022-05-23 | 7 | 2022-05-30
2.5 | Annual Survey Closes |  |  | Jaci |  |  | 100% |  | 2022-05-27 | 0 | 2022-05-27
2.6 | Consult Web Developer on Feasibility of web-based annural report |  | Erin | Layah | Jaci |  | 100% |  | 2022-05-31 | 0 | 2022-05-31
2.7 | SOW for graphic designer created (if needed) |  | Nancy | Erin | Layah |  | 0% |  | 2022-06-07 | 0 | 2022-06-07
2.8 | Consult giving levels to understand funder page of annual report | Link | Erin | Layah | Kirby | Project Team | 0% |  | 2022-06-01 | 7 | 2022-06-08
2.9 | Sign off on Stage Completed | [5 empty] | 0% |  |  | 0
3 | PROJECT EXECUTION | [5 empty] | 0% |  |  | 0
3.1 | Creative Development |  | Nancy | Layah |  |  | 50% |  | 2022-05-31 | 7 | 2022-06-07
3.2 | Gather impact stories from team |  | Nancy | Layah | Cait B | All Teams | 80% |  | 2022-05-31 | 14 | 2022-06-14
3.3 | CEO to write welcome letter |  | Layah | Mel |  |  | 100% |  | 2022-06-14 | 10 | 2022-06-24
3.4 | Receive estimate/SOW from web designer |  | Jaci | Layah |  |  | 0% |  | 2022-06-03 | 4 | 2022-06-07
3.5 | Confirm work to be completed by web developer |  | Layah | Jaci |  |  | 0% |  | 2022-06-08 | 0 | 2022-06-08
3.6 | Vet graphic designer(s) (if needed) |  | Erin | Layah |  |  | 0% |  | 2022-06-06 | 7 | 2022-06-13
3.7 | Sign contract with graphic designer (if needed) |  | Erin | Layah |  |  | 0% |  | 2022-06-17 | 0 | 2022-06-17
3.8 | Mockup content on web (lorem ipsum) |  | Erin | Layah |  |  | 0% |  | 2022-06-20 | 7 | 2022-06-27
3.9 | Flow content on web |  | Erin | Layah |  |  | 0% |  | 2022-06-27 | 7 | 2022-07-04
3.10 | Collection of 10k+ partner logos |  | Layah | Kirby |  |  |  |  | 2022-06-24 | 28 | 2022-07-22
3.11 | Initial Stakeholder Review |  | Erin | Cait B |  |  | 0% |  | 2022-07-11 | 7 | 2022-07-18
3.12 | Stakeholder feedback implemented |  | Erin | Layah |  |  | 0% |  | 2022-07-19 | 3 | 2022-07-22
3.13 | Update sponsors page of website to reflect 10k+ donors | Website | [6 empty] | 2022-07-18 | 4 | 2022-07-22
3.14 | Annual Report sent for translations |  | Erin | Layah |  |  | 0% |  | 2022-07-25 | 4 | 2022-07-29
3.15 | Final review |  | Layah | Nancy |  |  | 0% |  | 2022-08-02 | 3 | 2022-08-05
3.16 | Share update in CLC weekly email |  | Erin | Layah |  |  | 0% |  | 2022-08-17 | 0 | 2022-08-17
3.17 | Go live |  | Nancy | Layah |  |  | 0% |  | 2022-08-19 | 0 | 2022-08-19
3.18 | [MARKETING/DISTRIBUTION TASKS] | [5 empty] | 0% |  |  | 0
3.19 | [6 empty] | 0% |  |  | 0
3.20 | [6 empty] | 0% |  |  | 0
3.21 | Sign off on Stage Completed | [5 empty] | 0% |  |  | 0
4 | PROJECT MONITORING & CONTROLLING | [5 empty] | 0% |  |  | 0
4.1 | Monitor social activity on the posts |  |  | Layah |  |  | 0% |  |  | 0
4.4 | Collect google analytics of web traffic |  |  | Layah |  |  | 0% |  |  | 0
4.5 | Tasks | [5 empty] | 0% |  |  | 0
4.6 | Tasks | [5 empty] | 0% |  |  | 0
4.7 | Tasks | [5 empty] | 0% |  |  | 0
4.8 | Tasks | [5 empty] | 0% |  |  | 0
4.9 | Sign off on Stage Completed | [5 empty] | 0% |  |  | 0
5 | PROJECT CLOSING | [5 empty] | 0% |  |  | 0
5.1 | Create impact report |  |  | Layah |  |  | 0% |  |  | 0
5.2 | Create lessons learned document |  | Layah | Erin |  |  | 0% |  |  | 0
5.3 | Finalize and file all project documents |  |  | Erin |  |  | 0% |  |  | 0
5.4 | Budget vs. actuals updated |  |  | Layah |  |  | 0% |  |  | 0
5.5 | Tasks | [5 empty] | 0% |  |  | 0
5.6 | Tasks | [5 empty] | 0% |  |  | 0
5.7 | Tasks | [5 empty] | 0% |  |  | 0
5.8 | Tasks | [5 empty] | 0% |  |  | 0
5.9 | Sign off on Stage Completed | [5 empty] | 0% |  |  | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Goals
Goal | Measure | Tracking | Variance | Notes
Annual Report Complete | Y/N | N |  | Link

## Action Items
# | Owner | Item | Date Assigned | Due Date | Status | Done | Notes
1 | [5 empty] | FALSE
2 | [5 empty] | FALSE
3 | [5 empty] | FALSE
4 | [5 empty] | FALSE
5 | [5 empty] | FALSE
6 | [5 empty] | FALSE
7 | [5 empty] | FALSE
8 | [5 empty] | FALSE
9 | [5 empty] | FALSE
10 | [5 empty] | FALSE
11 | [5 empty] | FALSE
12 | [5 empty] | FALSE
13 | [5 empty] | FALSE
14 | [5 empty] | FALSE
15 | [5 empty] | FALSE
16 | [5 empty] | FALSE
17 | [5 empty] | FALSE
18 | [5 empty] | FALSE
19 | [5 empty] | FALSE
20 | [5 empty] | FALSE
21 | [5 empty] | FALSE
22 | [5 empty] | FALSE
23 | [5 empty] | FALSE
24 | [5 empty] | FALSE
25 | [5 empty] | FALSE
26 | [5 empty] | FALSE
27 | [5 empty] | FALSE
28 | [5 empty] | FALSE
29 | [5 empty] | FALSE
30 | [5 empty] | FALSE
31 | [5 empty] | FALSE
32 | [5 empty] | FALSE
33 | [5 empty] | FALSE
34 | [5 empty] | FALSE
35 | [5 empty] | FALSE
36 | [5 empty] | FALSE
37 | [5 empty] | FALSE
38 | [5 empty] | FALSE
39 | [5 empty] | FALSE

## Decision Log
# | DECISION DATE | STATUS | DECISION MAKER | WHO CONTRIBUTED TO DECISION | WHAT IS THE DECISION? | WHY MAKE THIS DECISION | WHAT CHOICES DID YOU CONSIDER? WHY THIS DECISION? | COMMUNICATED TO PROJECT TEAM? | NEXT STEPS
1 | [7 empty] | FALSE
2 | [7 empty] | FALSE
3 | [7 empty] | FALSE
4 | [7 empty] | FALSE
5 | [7 empty] | FALSE
6 | [7 empty] | FALSE
7 | [7 empty] | FALSE
8 | [7 empty] | FALSE
9 | [7 empty] | FALSE
10 | [7 empty] | FALSE
11 | [7 empty] | FALSE
12 | [7 empty] | FALSE
13 | [7 empty] | FALSE
14 | [7 empty] | FALSE
15 | [7 empty] | FALSE
16 | [7 empty] | FALSE
17 | [7 empty] | FALSE
18 | [7 empty] | FALSE
19 | [7 empty] | FALSE
20 | [7 empty] | FALSE
21 | [7 empty] | FALSE
22 | [7 empty] | FALSE
23 | [7 empty] | FALSE
24 | [7 empty] | FALSE

## RAID
# | DATE IDENTIFIED | TYPE | DESCRIPTION | IMPACT | PROBABILITY | MITIGATIONS/NEXT STEPS | ADDED BY | ACTION NEEDED BY | FOLLOW UP DATE | RESOLVED/DISCUSSED?
1 | [9 empty] | FALSE
2 | [9 empty] | FALSE
3 | [9 empty] | FALSE
4 | [9 empty] | FALSE
6 | [9 empty] | FALSE
5 | [9 empty] | FALSE
7 | [9 empty] | FALSE
8 | [9 empty] | FALSE
9 | [9 empty] | FALSE
10 | [9 empty] | FALSE
11 | [9 empty] | FALSE
12 | [9 empty] | FALSE
13 | [9 empty] | FALSE
14 | [9 empty] | FALSE
15 | [9 empty] | FALSE
16 | [9 empty] | FALSE
17 | [9 empty] | FALSE
18 | [9 empty] | FALSE
19 | [9 empty] | FALSE
20 | [9 empty] | FALSE
21 | [9 empty] | FALSE
22 | [9 empty] | FALSE
23 | [9 empty] | FALSE
24 | [9 empty] | FALSE
25 | [9 empty] | FALSE
26 | [9 empty] | FALSE
27 | [9 empty] | FALSE
28 | [9 empty] | FALSE
29 | [9 empty] | FALSE
30 | [9 empty] | FALSE

## Meeting Minutes (hidden)
[TEMPLATE] Date: XXXX Notetaker: XXX Action Items Lister: XXXX Shoutouts [3 mins]: - - - Progress Towards Goals [5 minutes] Special Agenda + Discussion Items [15 mins]: - - - RAID (Risks, Assumptions, Issues, Dependencies) Review [35 mins]: RAID Discussion Notes: [1] [2] [3] Action Items Review [2 mins]:

## Status Update (hidden)
📅 Status Update for the Week … cc/ @informed ✨ Project Highlights ... 👀 Focus Areas Going Forward ….. 🔒 Decisions Made …... ⛰️ Challenges/Risks ….. ❓ Feel free to reach out with any questions!

## Roles
ROLE | TEAM MEMBER (S) | DESCRIPTION OF ROLE | CORE OR EXTENDED TEAM?

## Lessons Learned
Type | Category | Description | Factors that supported the success / Recommended Solutions | Date Added | Name

## Change Log
*Note this form goes to column O
No. | Date | Requested by | Category | Task | Description | Precursor (what lead to this) | Justification/Rationale (Why make the change) | Dependencies | Other team(s) involved | Risk | Suggested implementation if approved | Action Items | Approval Needed by | Approved
1 | [13 empty] | FALSE
2 | [13 empty] | FALSE
3 | [13 empty] | FALSE
4 | [13 empty] | FALSE
5 | [13 empty] | FALSE
6 | [13 empty] | FALSE
7 | [13 empty] | FALSE
8 | [13 empty] | FALSE
9 | [13 empty] | FALSE
10 | [13 empty] | FALSE
11 | [13 empty] | FALSE
12 | [13 empty] | FALSE
13 | [13 empty] | FALSE
14 | [13 empty] | FALSE
15 | [13 empty] | FALSE
16 | [13 empty] | FALSE
17 | [13 empty] | FALSE
18 | [13 empty] | FALSE
19 | [13 empty] | FALSE
20 | [13 empty] | FALSE

## Cost Tracking
Total Project Budget: [XXX]
Actual cost to date: |  | 0
Estimate to date: |  | 0
Estimate | COST($) | Per Unit | # of units | Actuals | DESCRIPTION | BUDGET | DATE | APPROVAL NEEDED | APPROVED | NOTES | RELATED DOCS
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Inputs
TEAM MEMBER NAME | PHASE | ARCI | TEAM | STATUS | RISK LEVEL | A RISK? | CRITICALITY LEVEL | RISK CATEGORY | TYPE | RISK DEFINITION | Category | Lessons Learned | Type
CEO | Analysis | Accountable | People and Culture | New | Low | Yes | Low | Strategic Risk | Risk | Market Risks - The ability of CLC to continue its operation in line with its strategic objectives | Technology | Success | Scope
COO | Procurement | Responsible | Design & Training | Not Started | Moderate | No | Moderate | Operational Risk | Issue | Business Growth Risks – The ability of the organization to maintain execute needed activities related to growth, new partnership and affiliations | Content | Shortcoming | Cost
CPO | Planning | Consulted | CS&P | In Progress | High |  | High | Financial Risk | Dependency | Reputational Risks - the potential loss to financial capital, social capital and/or market share resulting from damage to CLC's reputation. | Delivery |  | Time
Dir D&T | Preparation | Informed | Fund Development | At Risk | Catastrophic |  | Critical | MLE Risk | Assumption | Human Resources or People Risks - Insufficient capability or capacity | Administration |  | Team Management
Dir CS&P | Configuration |  | Finance | Blocked | [5 empty] | Information Security - Data Security, confidentiality, privacy or integrity is compromised | Marketing |  | Task Scope
Dir FundDev | Integration |  | Operations | Postponed | [5 empty] | Business Interruption Risk -The inability to recover systems and services, in a timely manner, following an internal or external event which disrupts normal operations | Reporting/Evaluation
K-12 PM | Migration |  | Brand | Complete | [5 empty] | Program Design Risks - Risks associated with the design of our experiences | Design
Adult PM | Testing |  | SLT | [6 empty] | Program Delivery Risks - Risks associated with the delivery of our experiences | Strategy
CSMs - ALL | Go Live |  | Executive Sponsor | [6 empty] | Revenue & Expenses Risk - Insufficient/inappropriate spending or revenue generation
Project Manager | Adoption |  | Learning Experience Team | [6 empty] | Financial Crime Risk - Activity which attempts to, or successfully secures an illegal financial benefit either internal or external including fraud, money laundering and rouge trading
CSM - Chapter | Approval |  | LMS Content Team
Chapter Lead | Implementation |  | LMS Administrator(s)
CSM - CodeSquad | Notification |  | UX/UI Team
Code Squad | Communication |  | Usability Specialist
Comms Leads | Transfer |  | IT Architect(s)
Ed Leads | Wrap-up |  | IT/ Learning Technology Team
Code Squad Adult Team | Prep & Plan |  | Extended Project Team
Code Squad Youth Team East
Code Squad Youth Team West
Marketing Manager
Operations Manager
Software Administrator
Content Development Manager
Instructor Training Lead
Operations and Marketing Coordinator
Content Design Lead
Content Developer
Trainer and Technical Support Lead
Project Team
All Teams
SLT
Managers
People and Culture
Design & Training
Community Success & Partnerships
Fundraising
Finance
Operations
Brand Strategy
Proofreader
Translation
DirBrand
Executive Sponsor
Learning Experience Team
LMS Content Team
LMS Administrator(s)
UX/UI Team
Usability Specialist
IT Architect(s)
IT/ Learning Technology Team
Extended Project Team
Core Project Team
Ana
Cait B
Erin
Fanny
Jaci
Layah
Nancy
Mel
Lucie
Laura
Nicole
Lisa
Angela
Kirby
Ashley
Name
Name
Name
Name